## Transmittal Form
COBie-FORMATTED TRANSMITTAL FORM |  |  |  | DATE: | 2019-05-15 08:31 | TRANSMITTAL NO.: | 23 81 00 - 01
SECTION 1. HEADER
| TO: | Galliford Try |  |  | FROM: | SES (Engineering Services)
|  | (ATTN:John Ford) |  |  |  | (ATTN: Gavin Dunstan)
|  | C&I North Scotland, Shand House |  |  |  | First Floor, 184-192 Drummond Street
|  | Derbyshire, Matlock DE4 3AF UK |  |  |  | London NW1 3HP UK
|  | 0752 222 7897 |  |  |  | 2073801800
|  | John.Ford@Gallifordtry.co.uk |  |  |  | gdunstan@ses-ltd.co.uk
SECTION 2. SUBJECT
| Project: | Four Dormitory Complex |  |  | Spec. Section: | 23 81 00 00 20 - UNITARY AIR CONDITIONING EQUIPMENT 11/09
| ID: | East Dormitory
SECTION 3. ACTION
| Action Reqd.: | Contractor Certified
| Comments: | (1) AHU has 3 connections but only Supply Extract and Intake are shown. Provide method of Exhaust discharge. (2) This unit is not factory tested prior to shipping.
| Action: | Initial
| Submitted By: | G Dunstan |  | Date Submitted: | 2019-05-15 08:31 |  | Date Required: | 2019-06-29 08:31
Action Taken:
Action Comment:
Action By:
SECTION 4. PRODUCT TYPES AND DATA (one sub-section required per product type)
Section 4.1 | Action: | Product Type: | Manufacturer | Model Number |  | Supplier
| Initial | Air Handling Unit (Air Handling Unit_63300000 J) | VES Andover Ltd | MAX37/A/SW/S |  | VES Andover Ltd
Attached Data Files
| Product Data: | Air Handling Unit.pdf
| Mfg Test Report: | n/a
| Mfg Warranty: | Air Handling Unit Warranty.pdf
| Instructions: | Air Handling Unit Operation.pdf
| Maintenance Manual: | Air Handling Unit O&M.pdf
| Replacement Parts: | Air Handling Unit Warranty.pdf
| Field Test Reports: | n/a
| Accessory Products | Accessory Name | Attached Data file
| Product Data: | Fitted & Pre-Wired Isolator To Suit 1 No. Damper Motor | Air Handling Unit.pdf
| Product Data: | 24V Open Close Damper Motor | Air Handling Unit.pdf
| Product Data: | Filter Pressure Switch - Fitted | Air Handling Unit.pdf
| Product Data: | Magnehelic Gauge To Suit 0-250 Pa | Air Handling Unit.pdf
| Product Data: | Airflow Pressure Switch - Fitted | Air Handling Unit.pdf
| Product Data: | ELGN1050 Motor Isolator Supplied Fitted & Pre-Wired | Air Handling Unit.pdf
| Product Data: | Filter Pressure Switch - Fitted | Air Handling Unit.pdf
| Product Data: | Magnehelic Gauge To Suit 0-250 Pa | Air Handling Unit.pdf
| Product Data: | Airflow Pressure Switch - Fitted | Air Handling Unit.pdf
| Product Data: | ELGN1050 Motor Isolator Supplied Fitted & Pre-Wired | Air Handling Unit.pdf
| Product Data: | Fitted & Pre-Wired Isolator To Suit 1 No. Damper Motor | Air Handling Unit.pdf
| Product Data: | 24V Open Close Damper Motor | Air Handling Unit.pdf
Lean Handover(TM) Templates |  |  | (c)2016-9 Prairie Sky Consulting |  |  | www.prairieskyconsulting.com

## Company
Category | PickCompany | Street | City | StateRegion | Country | PostalCode | Phone | Email | Website
PM_20_20_67 : Project manager | Galliford Try | C&I North Scotland, Shand House | Matlock | Derbyshire | UK | DE4 3AF | 0752 222 7897 | John.Ford@Gallifordtry.co.uk | www.Gallifordtry.co.uk
PM_20_20_85 : Sub-contractor | SES (Engineering Services) | First Floor | 184-192 Drummond Street | London | UK | NW1 3HP | 2073801800 | gdunstan@ses-ltd.co.uk | www.ses-ltd.co.uk
PM_20_20_54 : Manufacturer | VES Andover Ltd | Eagle Close, Chandlers Ford Industrial Estate | Eastleigh | Hampshire | UK | SO53 4NF | 08448 151660 | vesltd@ves.co.uk | www.ves-online.co.uk

## Pick List (hidden)
Submittal Action | Form Action | Role
Initial | Contractor Certified | PM_20 : Personnel
Revision | Information Only | PM_20_10 : Organization roles
Addition | Owner Approval | PM_20_10_05 : Associate
Deletion |  | PM_20_10_12 : Chairman
PM_20_10_14 : Chief executive officer
PM_20_10_16 : Chief financial officer
PM_20_10_18 : Chief operating officer
PM_20_10_25 : Director
PM_20_10_30 : Executive director
PM_20_10_50 : Manager
PM_20_10_53 : Managing director
PM_20_10_58 : Non-executive director
PM_20_10_60 : Partner
PM_20_10_65 : President
PM_20_10_94 : Vice chairman
PM_20_10_95 : Vice president
PM_20_20 : Asset management and delivery roles
PM_20_20_01 : Access consultant
PM_20_20_04 : Asset manager
PM_20_20_11 : Catering consultant
PM_20_20_13 : Clerk of works
PM_20_20_14 : Client
PM_20_20_15 : Client advisor
PM_20_20_16 : Client representative
PM_20_20_18 : Construction operative
PM_20_20_19 : Contract administrator
PM_20_20_20 : Contractor
PM_20_20_22 : Cost consultant
PM_20_20_26 : Employer
PM_20_20_27 : Employer's agent
PM_20_20_28 : Energy consultant
PM_20_20_30 : Facilities manager
PM_20_20_36 : Health and safety consultant
PM_20_20_40 : Importer
PM_20_20_42 : Information manager
PM_20_20_43 : Insurance consultant
PM_20_20_47 : Legal consultant
PM_20_20_50 : Maintenance provider
PM_20_20_52 : Management consultant
PM_20_20_54 : Manufacturer
PM_20_20_56 : Nominated supplier
PM_20_20_65 : Procurement consultant
PM_20_20_67 : Project manager
PM_20_20_74 : Safety manager
PM_20_20_76 : Security consultant
PM_20_20_85 : Sub-contractor
PM_20_20_86 : Supplier
PM_20_20_88 : Traffic consultant
PM_20_20_90 : Transportation consultant
PM_20_30 : Statutory roles
PM_20_30_09 : Building control officer
PM_20_30_16 : Conservation officer
PM_20_30_26 : Environmental officer
PM_20_30_36 : Heritage officer
PM_20_30_60 : Party wall surveyor
PM_20_30_65 : Planning officer
PM_20_30_67 : Principal contractor
PM_20_30_68 : Principal designer
PM_20_40 : Team lead roles
PM_20_40_04 : Asset management lead
PM_20_40_19 : Construction lead
PM_20_40_25 : Design lead
PM_20_40_61 : Operation lead
PM_20_40_69 : Programme lead
PM_20_40_70 : Project lead
PM_20_50 : Design roles
PM_20_50_02 : Acoustic engineer
PM_20_50_03 : Architect
PM_20_50_04 : Architectural designer
PM_20_50_05 : Architectural technologist
PM_20_50_08 : Building services engineer
PM_20_50_11 : Civil engineer
PM_20_50_14 : Cladding designer
PM_20_50_17 : Commissioning engineer
PM_20_50_24 : Demolition engineer
PM_20_50_28 : Drainage engineer
PM_20_50_30 : Electrical services engineer
PM_20_50_33 : Fire engineer
PM_20_50_41 : Highways engineer
PM_20_50_43 : Interior designer
PM_20_50_47 : Landscape architect
PM_20_50_48 : Landscape designer
PM_20_50_50 : Lighting designer
PM_20_50_53 : Mechanical, electrical, instrumentation, control and automation (MEICA) consultant
PM_20_50_54 : Mechanical services engineer
PM_20_50_69 : Process engineer
PM_20_50_73 : Public health engineer
PM_20_50_76 : Rail engineer
PM_20_50_77 : Road engineer
PM_20_50_80 : Signage designer
PM_20_50_83 : Structural engineer
PM_20_50_90 : Telecommunication engineer
PM_20_50_96 : Water services engineer
PM_20_70 : Surveyor and planner roles
PM_20_70_10 : Building inspector
PM_20_70_11 : Building surveyor
PM_20_70_16 : Conservation surveyor
PM_20_70_26 : Environmental surveyor
PM_20_70_36 : Heritage surveyor
PM_20_70_37 : Geotechnical surveyor
PM_20_70_46 : Land surveyor
PM_20_70_64 : Planning consultant
PM_20_70_75 : Quantity surveyor
PM_20_70_80 : Site investigation consultant
PM_20_70_85 : Survey specialist
PM_20_70_93 : Utilities surveyor
PM_20_80 : Environmental and geological roles
PM_20_80_04 : Archaeologist
PM_20_80_25 : Ecologist
PM_20_80_27 : Environmental assessor
PM_20_80_28 : Environmental consultant
PM_20_80_35 : Geographic information system consultant
PM_20_80_37 : Geotechnical consultant
PM_20_80_85 : Sustainability consultant